## Sheet1
| Root Agenda Date |  |  |  |  | 2015-02-13 | 2015-03-06 | 2015-04-06 |  | 2015-05-04 | 2015-06-03 | 2015-07-06 | 2015-07-20 | 2015-08-05 | 2015-08-21 | 2015-09-04 | 2015-09-21
Thief River Watershed One Watershed, One Plan
Proposed Schedule as of June 13, 2018 PWG/AC/PC Meeting
Meeting Number |  | 1 | 2* | 3 | 4 | 5 | 6* | 7 | 8 | 9 | 10* | 11 | 12 | 13 | 14* | 15 | 16 | 17 | 18 | 19 | 20 | 21
Meeting Type (IP=In-person, CC=Conference Call) |  | IP | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Meeting Attendees (PWG=Planning Work Group, AC=Advisory Committee, PC=Policy Committee) |  | PWG, AC, PC | PWG/AC | PWG/PC | PWG/AC | PWG/PC | PWG/AC | PWG/PC | PWG/AC | PWG/PC | PWG/AC | PWG/PC | PWG/AC | PWG/PC | PWG/AC | PWG/PC | PWG/AC | PWG/PC | TBD | TBD | TBD | TBD
Year |  | 1: 2017; 6*: 2018; 18: 2019
Month |  | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April
Meeting Date |  | 18 | 13 | 11 | 8 | 13 | 10 | 14 | 14 | 11 | 9 | 13 | 11 | 8 | 12 | 10 | 14 | 12 | 9 | 12 | 12 | 10
Task 1. Selection of Plan Consultant (Completed by Local Staff and Local Planning Committees pior)
Task 2. Committees, Notifications, and Initial Planning Meeting
Task No. 2.3: Aggregate watershed information and review for commonalities, conflicts, and gaps
1W1P Vision (Presentation) |  | 2017 August: Present
Meeting Schedule |  | 2017 August: Decide
Participation Plan |  | 2017 August: Intro/Discuss; 2017 September: Decide
Plan Outline |  | 2017 August: Decide
Draft Prioritization Matrix |  | 2017 August: Introduce
Task 3. Draft the Plan
Task No. 3.1: Draft Plan ‐ Continue to aggregate watershed information
Prioritization Matrix |  | 2017 August: Introduce; 2017 September: Discuss; 2017 November: Decide
Section 1: Introduction |  | 2017 December: Introduce; 2018 January: Discuss; 2018 February: Decide
Land and Water Resources Inventory |  | 2017 October: Introduce; 2017 December: Discuss; 2018 January: Decide
Task No. 3.2: Draft Plan‐ Analyze and Prioritize Issues
Prioritization Process |  | 2017 September: Intro/Discuss; 2017 October: Decide; 2018 January: Implement; 2018 March: Decide
Resource Concern and Issues: Maps |  | 2017 September: Introduce; 2017 December: Discuss; 2018 January: Decide
Emerging Concerns |  | 2017 November: Intro/Discuss; 2017 December: Discuss; 2018 January: Decide
Section 2: Identification and Prioritization of Resources |  | 2018 January: Intro/Discuss; 2018 February: Discuss; 2018 March: Discuss; 2018 April: Decide
Task No. 3.3: Draft Plan‐ Establish Measurable Goals
Format: Measurable Goals, Strategies, and Actions |  | 2017 October: Introduce
Strategies and Actions |  | 2017 October: Introduce; 2018 February: Discuss; 2018 April: Discuss
Measurable Goals |  | 2017 December: Introduce; 2018 January: Discuss; 2018 February: Discuss; 2018 April: Discuss
Protection / Restoration Definitions and Mapping |  | 2017 November: Intro/Discuss; 2018 January: Discuss; 2018 February: Discuss; 2018 March: Discuss
Section 3: Establishment of Measurable Goals |  | 2018 April: Introduce; 2018 May: Discuss; 2018 June: Decide
Task No. 3.4: Draft Plan ‐ Develop a targeted and measurable implementation schedule and programs
Additional Analysis (i.e. Nitrate Infiltration Risk Maps) |  | 2018 April: Introduce
Targeted Implementation Schedule |  | 2018 May: Introduce; 2018 June: Discuss; 2018 July: Discuss; 2018 August: Decide
Model / Tool Implementation Approach |  | 2017 December: Discuss; 2018 January: Discuss; 2018 February: Discuss; 2018 March: Discuss; 2018 April: Discuss; 2018 May: Discuss; 2018 June: Discuss; 2018 July: Discuss; 2018 August: Decide
Targeted Implementation Plan (from model / tool results) |  | 2018 July: Discuss; 2018 August: Decide
Section 4: Targeted Implementation Schedule |  | 2018 July: Introduce; 2018 August: Discuss; 2018 September: Decide
Implementation Programs; Capital Improvements |  | 2017 December: Introduce; 2018 January: Discuss; 2018 February: Discuss; 2018 June: Discuss; 2018 July: Decide
Section 5: Implementation Programs |  | 2018 June: Introduce; 2018 July: Discuss; 2018 August: Discuss; 2018 September: Decide
Task No. 3.6: Draft Plan‐ Write Plan Final review draft
Executive Summary |  | 2018 August: Introduce; 2018 September: Decide
Drafted Final Plan |  | 2018 October: Introduce; 2018 November: Decide; 2018 December: Decide; 2019 January: Decide (PC)
4. Formal Plan Review and Public Hearing
Task No. 4.1 (Formal review) and 4.2 (Public Hearing) |  | 2018 April: Discuss; 2018 May: Discuss; 2018 June: Decide; 2018 November: Completed by Local Staff / Planning Committees
Task No. 4.3: Write Final Plan |  | 2019 March: Introduce; 2019 April: Decide
Tasks 5 (Plan Approval by BWSR), 6 (Local Adoption), and 7 (Grant Reporting) of Workplan to be completed by Local Staff and Local Planning Committees
Regular Meeting Times |  | 2017 September: 9:00AM to Noon
Notes: | "Introduce, Discuss, Decide" primarily relates to PWG meetings, and is intended to set planning process pace. AC and PC members will review and approve developed material as available.
Schedule is intended to document planning pace of progress and anticipated scheduled meetings. However, meeting dates and meeting committees may change to meet planning process needs.
* Denotes a meeting that will be held in Grygla